## Taul1
Work tracking sheet |  |  |  | Name: | Florian Brandsma
Signature:
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
27.11.2017 | 14:15 | 15:45 | 1:30 | 1:30 | Set up GIT repository. Start project planning.
28.11.2017 | 9:15 | 12:30 | 3:15 | 4:45 | Finish project planning. Start making mockups.
29.11.2017 | 8:15 | 13:00 | 4:45 | 9:30 | Finish mockups. Showed to Veijo for feedback. Start implementing feedback for final UI design.
30.11.2017 | 9:15 | 14:00 | 4:45 | 14:15 | Finish final UI design. Start experimenting with Javascript.
04.12.2017 | 10:00 | 17:45 | 7:45 | 22:00 | Creating number system convertion functions.
05.12.2017 | 10:00 | 15:00 | 5:00 | 27:00 | Implement convertion functions in number system outputs table.
07.12.2017 | 09:15:00 20:00 | 15:30:00 22:00 | 8:15 | 35:15 | Finish random value javascript. Create truth table algorithm.
08.12.2017 | 9:30 | 14:45 | 5:15 | 40:30 | Implement truth table algorithm in table form.
11.12.2017 | 11:00 | 17:15 | 6:15 | 46:45 | Added Number System Converter functionality. Continue work on Truth Table.
14.12.2017 | 14:30:00 20:00 | 15:30:00 24:00 | 5:00 | 51:45 | Added dropdowns in Truth Table. Further develop calculations in truth table.
15.12.2017 | 11:00:00 20:00 | 16:45:00 0:00 | 9:45 | 61:30 | Project report. Finished truth table code.
16.12.2017 | 13:00:00 20:30 | 17:30:00 01:45 | 9:45 | 71:15 | Truth table bug fixes. Create temperature converter. Clean existing code.
17.12.2017 | 13:30 | 20:00 | 6:30 | 77:45 | Made Temperature Converter user-friendlier. Removed errors in code. Created Combinatorics tool. Added filter to Number System Converter. Polished results and made presentation.