## Taul1
Work tracking sheet |  |  |  | Name: | Oleksandr Gudenko
Signature:
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
27.11.2017 | 14:15 | 15:45 | 1:30 | 1:30 | Started to work on Project plan and got git repository ready.
28.11.2017 | 9:15 | 12:30 | 3:15 | 4:45 | Finishing Project Plan, stated working on Project Mockups
29.11.2017 | 8:15 | 13:00 | 4:45 | 9:30 | Finishing Mockups, choosing Final design solution
30.11.2017 | 9:15 | 14:00 | 4:45 | 14:15 | Finilization of Mochups. Start of Web page design.
04.12.2017 | 8:00 | 16:50 | 8:00(exlucding lunch) | 24:15 | Further web page development.
05.12.2017 | 9:15 | 15:00 | 5:45 | 30:00 | Web Page UI&Navigation development.
07.12.2017 | 9:15 | 15:30 | 6:15 | 36:15 | Web Page UI&Navigation development. Element alignment.
08.12.2017 | 10:00 | 14:30 | 4:30 | 40:45 | RandomValue page done. Layout improvements.
11.12.2017 | 9:15 | 17:15 | 8:00 | 48:45 | Minor fixes. TemperatureConverter layout/formules.
12.12.2017 | 10:00 | 14:05 | 4:05 | 52:50 | Major fixes. TemperatureConverter layout modified.
14.12.2017 | 14:00 | 15:35 | 1:30 | 54:20 | Combinatorics page created.
15.12.2017 | 9:45 | 16:45 | 8:00 | 62:20 | TruthTable layout improvements. Combinatorics layout. Project report.
16.12.2017 | 11:30 | 14:40 | 3:00 | 65:20 | TruthTable layout complete. Code improvements.
17.12.2017 | 15:30 | 20:00 | 4:30 | 70:20 | Fixed issues with layout alignment in Chorme&Firefox. Additional layout improvements